# Case Study 1: Creating Agile Resources for University Instructors Teaching Online

by

Kathy Schwalbe

Draft created July 2020

Copyright 2020 Schwalbe Publishing

Note: This case is based on the author’s personal experience.  It uses a modified scrum approach. Some of the information is real, and some is fictitious. It focuses on using agile to provide useful products quickly and to promote continuous learning.

### Part 1

Background Scenario:

Most new editions of university textbooks are written using a traditional approach to project management. Authors review user feedback on the current edition, research changes in the field, new certifications, etc., and update the book, usually focusing on one chapter at a time. After several reviews and edits, the new edition is then published.  New editions are published every 2-4 years. If working with a large publishing firm, the process to produce a new edition often takes at least a year. In self-publishing, the timeline is much shorter, often 2-4 months.

Assume you are the author of several popular project management textbooks. Several instructors and students have asked for new information they need before classes start next semester. For example, most instructors have had to start teaching totally online (due to the pandemic), and students want more information on agile so they can apply it to their jobs and understand it in preparation for the new PMP exam, which will include more agile-based questions. Online classes are starting in 1-2 months, and the new exam starts in 5 months.

You decide to use a scrum framework, but you will modify it as needed for this project. For example, in scrum resources are usually dedicated, paid professionals with distinct roles who often work in a face-to-face environment. For this project, none of the resources will be full-time, they are all volunteers, and they will be working virtually.  Even you will not be working full-time on this project, and you will be doing the bulk of the work as the product owner, scrum master (sometimes called team leader or project manager), as well as a working team member. You define two major products: updates to your textbook’s website (providing some free exercises, quizzes, and two case studies) and a new instructor resource with 4 additional case studies and sample solutions for all 6 cases. Assume other team members will include at least two instructors/colleagues currently using your books, at least two agile practitioners working in the field, and at least two students interested in learning more about agile. About a week before this project officially started, you contacted four people who volunteered to help you after posting a message about it on LinkedIn. Elena and Jeff (fellow educators), Najwa (a former student of yours and scrum master for a large bank), and Cindy (another former student with experience in traditional and agile project management at several companies.) After several initial emails and phone calls, you solidify your main team members.

Work with your teammates and instructor to perform all or just some of the following initiating tasks for this project.

Tasks

- Vision statement: As product owner, create a product vision statement for this project to describe what the project will provide for customers and users. Find more details here from scrum.org.  Use Geoffrey Moore’s two-sentence framework as follows: For (target customer) who (statement of need or opportunity), the (product name) is a (product category) that (key benefit, reason to buy). Unlike (primary competitive alternative), our product (statement of primary differentiation).

- Project charter: Research project charters for agile projects. Find at least 3 good references, and then develop your own template for creating one for this project. Note that the Agile Alliance suggests you do not use someone else’s template without modifying to fit your needs, and that it fit on a single page. Then use your template to prepare a project charter for the Agile Resources Project. Describe why you are doing the project, who benefits from it and how, what defines success for the project, and how the team will work together.

- Share your project charter with one other person/team in your class. Discuss how you can use ideas from each one to create an even better charter together. Share this updated charter with your instructor.

### Part 2:

You are ready to begin planning for your project. Work with your teammates and instructor to perform all or just some of the following planning tasks for this project.

- Product roadmap: As product owner, create a product roadmap to provide a high-level overview of the project’s products in a graphical timeline format.  Because this is a small project, also include release information in the same document. (Some projects have a separate release plan). In reviewing the background scenario, you decide to have 3 releases. The first release will provide a new Agile tab on your current textbook website with free exercises, quizzes, and two case studies. The second release will provide 2 additional case studies and their solutions as well as the solutions to the first two free case studies, and the third release will include 2 or more case studies with their solutions as well as one combined document with all of the exercises, cases, and solutions to be posted on the secure instructor site (and later included in your next edition).

- Product backlog: As product owner, create a prioritized product backlog. including at least 15 items, with some for each release. Create the backlog in a table format with columns for priority, item ID, description (entered as a user story), and a rough estimate of the number of hours to complete the item. (You decide to use hours instead of story points for this project.) You might want to watch the short video called “Scrum in 10 Minutes” created by Axosoft and research other information on scrum for more information. Use the format below for the description/user story. For example:

| Priority | ID | Description/User Story | Estimate (hours) |
| --- | --- | --- | --- |
| 1 | 12 | As a site visitor, I want to find the new agile information, so I can easily access these resources. | 1 |
| 2 | 7 | As an instructor, I want up-to-date exercises on agile, so I can use them in my online classes. | 24 |
| 3 | 14 | As an instructor, I want suggested solutions to all exercises, so I can grade them more easily. | 12 |
| Etc. |  |  |  |

- Sprint plan: As a team, create a sprint plan for the first sprint, with a goal of doing all the work needed for the first release. Assume the sprint will be 2 weeks in length. The sprint plan should list the items in the sprint backlog (from the product backlog – add more if you did not have many related to the first sprint). After selecting at least 3 items/user stories, break them down into tasks, as needed. For example, to create the agile exercises, you might want to provide guidelines for the exercises, write them, receive feedback on them, update them, etc. Include hour estimates for each task. For example:

| User story | Task | Estimate (hours) |
| --- | --- | --- |
| 7. As an instructor, I want up-to-date exercises on agile, so I can use them in my online classes. | 1. Create guidelines for the exercises 2. Write a draft of exercises 3. Provide feedback on the exercises 4. Update the exercises 5. Post the exercises to the book website | 1 12 8 2 1 |
| Etc. |  |  |

### Part 3:

Background Scenario:

You hold your first daily scrum via a Zoom meeting on Day 1 of the 2-week sprint. You review the sprint backlog and start volunteering for tasks. You volunteer to do many of them, especially the ones that involve developing guidelines for creating the exercises and cases.  The team suggests that you find several students to provide feedback on the exercises, two cases, and the quiz you plan to release at the end of this sprint, so you add a task for that work. Elena takes responsibility for it. Jeff suggests that the team use Jira software to keep track of the tasks in the sprint instead of sending them via email. Najwa and Cindy also use Jira and highly recommend it, discussing it for over 10 minutes. Jeff offers to set it up before the next scrum. He estimates it will take 1 hour for this task, and it can be finished that day. Cindy also suggests that you be sure to include a “definition of done” for each user story. She then takes about 10 minutes explaining what this means and providing examples of why it is important. You sense that some team members are getting impatient.

Work with your teammates and instructor to perform all or just some of the following executing tasks for this project.

Tasks:

- Daily scrum: Near the end of the Zoom call, you ask how everyone is feeling so far, suggesting Najwa go first. Najwa comments that the first daily scrum, although useful, was too long as it took almost an hour and she had a lot of work to do. She suggested that in her experience teams often did not need daily scrums. She suggested that they hold scrum meetings just 2 days a week and limit them to 15 minutes. Each person will report on what they completed what tasks they plan to complete, and what impediments they faced. You, as product owner and scrum master, will log any impediments and hold separate meetings as needed to resolve them. Jeff agrees that the meetings should be short, but he still think they should be held every day. Research how often real teams hold “daily scrums” and how they make sure they are effective. For example, what do you do if one or two team members cannot meet at the designated time on certain days? Summarize your findings in a short paper, podcast, or video.

- Managing conflicts: Elena has been working on one of the cases, while you are working on the other. Even though you created guidelines for the case, Elena is having a hard time writing hers. She believes your guidelines are unclear. Role play a one-on-one phone conversation you can have with Helena. Be creative. Document the dialog in a short paper, video, or podcast.

- Updating user stories: After getting initial feedback on the quiz from several volunteer students, your team realizes that the students did not like what you produced. If you did not already write a user story for creating the quiz, write one, assuming it was vague. Also, research using story cards to provide more detailed requirements. Assume the students said they would like to have a brief description of the quiz to know if they were prepared to take it. They also wanted explanations for the answers or some reference to understand why their answers were incorrect. They also wanted more than one 10-question quiz on agile. They suggested that you create several quizzes, perhaps with one based on them completing all the exercises and more advanced one based on PMI’s Agile Practice Guide. Write an updated user story with a story card to address these requirements.

### Part 4:

You continue working on and completing the first sprint. Work with your teammates and instructor to perform all or just some of the following executing tasks for this project.

- Burndown chart: You have completed the first week of your 2-week sprint. Find your own burndown chart tool and enter information into it, including work completed for one week. (Be creative with your entries.) Print out the burndown chart along with a brief explanation of what’s happening and how burndown charts are a useful tool for measuring work progress.

- Sprint review: Assume you held a sprint review meeting via Zoom to demonstrate the products produced at the end of the sprint. The Agile tab is up and running on the textbook’s website, where anyone can find several exercises, quizzes, and one case study. You, as product owner, are pleased with most of the work and thank everyone for their contributions. Right before the meeting, you decided that the second case study needed more work before posting it online. Elena was disappointed as she was responsible for completing it, but she did admit that it could be improved. You move that work to the next sprint. You are concerned that there may be problems with the additional case studies in the next two sprints as well. Create a short paper, video, or podcast describing how various team members responded to the sprint review and what you as product owner should do next to improve future work.

- Sprint retrospective: One of the principles of agile is for teams to reflect on how to become more effective and adjust its behavior according. It’s important to address people’s feelings as well as the work completed in the retrospective. Assume that Najwa only participated in half of the daily scrum meetings but still did the work she volunteered for, only two of the four student volunteers did a good job on completing their tasks, a few people who initially said they’d volunteer for tasks then asked for compensation for their work, and you personally spent much more time than you thought holding individual conversations with team members, clarifying your expectations, and editing work to meet your standards. You also want to design an easy way to get instructors and students using the free exercises, quizzes, and one case you posted online to provide meaningful feedback. Using these and your own assumptions, create a short paper, video, or podcast describing an action plan for improvements for the next sprint.