INSTRUCTOR:  	Professor Kathy Schwalbe, 314B Memorial

OFFICE HOURS:  	8:00-9:30 A.M. Tuesdays and Thursdays. In my office at school when class physically meets and online otherwise.  Also available before and after class and by e-mail and appointment.

PHONE:  		(612) 330-1766  	E-MAIL: schwalbe@augsburg.edu.

Note: I check emails daily except on Sundays!

WEBSITE: www.kathyschwalbe.com.  Most course info is on the book site or in Moodle.

TEXT:  	Kathy Schwalbe, An Introduction to Project Management, Sixth Edition (published in Sep 2017-includes Project 2016 guide).  You can find links to buy or rent the book, read the first chapter, and find templates, interactive quizzes, and other materials on the companion website from http://intropm.com. Lecture slides and other information are available in the Moodle site for this class because they are copyrighted and class specific.

OBJECTIVES:  The student who successfully completes this course:

- Understands the genesis of project, program, and portfolio management and their importance to enterprise success

- Describes the various approaches for selecting projects, programs, and portfolios

- Explains the main tasks involved in and outputs of initiating, planning, executing, monitoring and controlling, and closing projects

- Demonstrates knowledge of project management terms and techniques such as

- The triple constraint of project management

- The project management knowledge areas

- Tools and techniques of project management such as

- Selection methods

- Work breakdown structures

- Gantt charts, network diagrams, critical path analysis

- Cost estimates

- Earned value management

- Motivation theory and team building

- Etc.

- Applies project management concepts by working on a team project as project manager or active team member. Note: If the project is done for a group outside of Augsburg, students completing that project can get credit for the Augsburg Experience

- Uses Microsoft Project 2016, and other software to help plan and manage a project

- Demonstrates good oral presentation skills

- Learns to use virtual collaboration tools like Moodle and Google sites

- Appreciates the importance of good project management by sharing examples of good and bad project management and using knowledge and skills developed in this class in other settings

APPROACH:  Lecture, online activities, homework, in-class exercises, group discussion, presentations, exams, and team projects will be used to aid in understanding and application of project management.

EVALUATION:	  1.	Team project and in-class activities		22%

2.	Individual presentation			8%

3.	Homework					20%

4.	Exam 1, Chapters 1-5				20%

5.	Exam 2, Chapters 6-10, App A		20%

6.	Online quizzes and activities			10%

Final grades will be based on overall percentages with about 94% required for a 4.0, 89% for a 3.5, 84% for a 3.0, 79% for a 2.5, 74% for a 2.0, etc.  I set a standard and do not curve. It is your responsibility to do assignments and study for exams.

POLICIES:

Homework Assignments:

Students will volunteer or be asked to discuss homework due that class period. Late homework will not be accepted, so be aware of due dates.  We will use Moodle to upload HW, take quizzes, and do some online activities. Please name the files (one file per homework, please) with your last name and then HW1, HW2, etc. Read the homework descriptions carefully. If you have a special circumstance, let me know in advance. Homework assignments are to be done individually, not as groups. There is one extra credit homework assignment that you can do to make up for lost points. 100% is the maximum HW score.

Participation:

Students are expected to actively participate in class and online by asking questions, working on in-class and online exercises, giving presentations as individuals or as part of their team projects, and sharing personal experiences and opinions related to the topics discussed.  Students who do not participate up to expectations or miss more than 4.5 in-class hours without a pre-approved or written excuse will have their final grades reduced by one grade (i.e. 4.0 to 3.5). Be sure to contact me BEFORE you miss a class, if possible. Let me know about last minute emergencies via email or phone as soon as you can. Also, please do not use cell phones, laptops, or other devices in class unless you are asked to do so or if you use them for class work. Be present in class. We will not meet every class period since some work will be done as teams or online, as noted in the draft schedule. A lot of project work is done online, and I want to prepare you for the real world of work.

Makeup Tests:

Requests for makeup tests must be made in advance with the instructor or the student will get no credit for that item. Either leave a phone message or send an e-mail message in case of a last minute emergency and we’ll try to work things out.

Honesty:

In accordance with Augsburg's academic honesty policy, students will sign a statement at the beginning of the course and sign a "pledged" signature on each test to reaffirm student honesty. You will receive a 0 on any item if you are dishonest. Be sure to cite references properly and do your own work. Also make sure you are honest in everything you do relating to your team projects and online activities.

Presentations:

All college graduates need to develop good speaking skills, and this course meets part of Augsburg’s speaking skill requirement.  Each student will give one individual presentation in class and part of a team final project presentation.  The individual presentation should be a 10-15 minute presentation and include visual aids like PowerPoint slides, access to online resources, or use of other software. If the presentation is on a topic not related to the team project, it should cite at least three related articles or books (besides our textbook).  Include a reference page/slide at the end of the presentation or on the handout.  References must have an author, title, and date. Also note references, such as quotes, statistics, etc. on specific slides/pages. Upload your presentation in Moodle or on your team project website (for progress reports) before your presentation (counts for 5 points out of 100).  Presentations will be evaluated based on content, delivery, and response.  A copy of the evaluation sheet is provided on the last page of this syllabus. I will determine presentation grades soon after you present, and one of your classmates will also provide written feedback. If you change your scheduled presentation date without an approved excuse, your presentation grade will be reduced by 10%. Most individual presentations will be based on your team projects, such as one of the two progress reports.   Below are a few ideas for presentation topics:

- How to give a great presentation in a business setting

- How to collaborate on documents using Google Docs or other tools (include demo)

- Creating and sharing Google sites (or other websites)

- Project time tracking (using a Google spreadsheet and other approaches-include demo)

- Personal time management (including use of software tools)

- Understanding the Myers-Briggs Type Indicator (MBTI) and how it relates to project teams

- More on work breakdown structures

- What’s new in project management software/phone apps

- Project Management Professional (PMP) and Certified Associate in Project Management (CAPM) certification

- Careers in project management

- Advice from real project managers

- Examples of current/recent projects (i.e. local projects, Augsburg projects, global projects, etc.)

- A topic related to your team project besides the progress report

Team Projects:

The purpose of the team project is to use a structured approach to project management in a team setting (3-5 students/team). Examples include creating a business plan for a potential business, updating a company’s website, helping launch a new store, planning and running an event, preparing a research report for an organization, working on a case study in the text, etc. I normally let teams self-select and assign people to teams as needed after we decide on the projects. One person could take the lead on each task, but other team members should provide inputs and edit the work so it is consistent and of high quality and reflects a team effort. Each team member should plan to spend 20-40 hours total on the team project, including some time in class. You should plan to use some of our online class times for team meetings/work. If the project is done for someone outside of Augsburg, students can earn the Augsburg Experience. You must have the sponsor email or call me to approve the project after you propose it if you really want to work on it. The sponsor must provide feedback at least twice during the term, including a final assessment with inputs on grades. If you do not choose to work on a real project, teams will work on a case study from Appendix C (on creating a new business venture or the fixer upper case). You will store all project documents on a site either using Google sites, Basecamp, or the tool of your choice.

Team Progress Reports:

See Appendix C in your text and on Moodle for details. If you are working on a case study, I’ll provide instructions on which tasks you should have completed by the progress report dates and which ones to present. Be sure to meet with me if you are doing a case study to clarify expectations. All project information must be available online before you present, and leave the default setting as public viewing access or provide me, your team, and your sponsor with access if it must be a secure site. You can give me edit access if you like, otherwise I will provide feedback via comments or email. Please use my kathyschwalbe47@gmail.com email for Google site access as Augsburg’s accounts do not include Google sites. Note: I will collect team participation ratings with Exam 1, and you get to grade yourself and team members as part of HW7.

Final Project Notebooks

By the last day of class, each team will present a formal, final presentation and hand in a project notebook (stapled pages are fine or a slim cover – not a binder or I’ll take off a few points!). The presentation and info in the notebook should all be on the team website as well.  Note: Each team member must give part of the 20-30 minute final presentation. Organize the final notebook as follows:

- Cover page and detailed table of contents.  List the project name, team members, location of Google site, and date on the cover page of the notebook.  Be sure to number all pages (by hand is fine), which should match the table of contents.  You may include tabs or dividers between major sections of the notebook, too. Put the project report first, followed by your final presentation, then product-related documents, then project management documents, then progress reports, then communications with sponsor.

- A double-spaced 3-4-page project report.  Address the following questions in your report:  What did your team produce?  Was the project a success or not, and what was your criteria for determining success?  (Remember that should be defined in your project charter early in the project). What project management tools/documents did you use, and did they help? How close was your draft schedule and estimate of hours to the actual schedule and actual hours worked on the project?  What went right on the project?  What went wrong?  What did your team learn by working on this project?  How did you select the project manager? Did he/she do a good job at leading your team?  Would he/she like to be a project manager in the future? Did you work well as a team? What was your project sponsor’s final assessment of the project? Include some written feedback from the sponsor in your final report and presentation. See the sample customer acceptance form in your text for an example. Discuss the answers to these questions in your final project presentation and show/summarize the main products produced. If your project involves some type of event, show pictures/videos of the event.

- A hard copy of your final presentation.

- Hard copies of key product-related documents your team produced. For example, if you created a business plan, include that. If you developed a website, include copies of the main pages. If you held an event, include pictures of the event, promotional materials created, etc.

- Hard copies of the final charter, scope statement, Gantt chart, and other project management documents you created, incorporating any feedback from me or your sponsor.

- Hard copies of your progress reports, including all documents/slides created from them.

- A summary of communications with your sponsor, including their final assessment.

Part of the grade for the team project will be based on the team’s final presentation and progress reports, and part of grade will be based on the quality of the project and its notebook (one notebook per team, due the last day of class).  Team project managers will earn a small amount of extra credit for successfully leading their project teams.

Homework Assignments (all must be typed). One single-spaced page should be at least 500 words. Include a word count at the top of your paper for HW1 and HW3. If you do not include a word count or references, I will deduct 5 points for each. For other assignments requiring a one-to-two-page paper, check the word count on your own to make sure you write enough.

HW1: Summary of Project Management Websites (100 points)

The purpose of this assignment is to help familiarize you with the world of project management. Review PMI’s website (www.pmi.org) and read and summarize one article from PM Network  (a monthly magazine and the most recent full report called the Pulse of the Profession. Both are under the Learning tab. Write a two-page single-spaced paper (800-1200 words) summarizing the following, using one paragraph for each bulleted item:

- An introduction, including what you learned about project management in general

- A brief summary of and your opinion about PM Network and the article you read (include citation as a footnote or endnote)

- A brief summary and your opinion about the Pulse of the Profession report you read

Be sure to cite references for the articles (i.e. include the author, title of article, publication, date, url, etc.). Also include the word count at the top of the page. You’ll lose 5 points for each if you do not include complete references or a word count.

HW2: Team Project Proposal (100 points)

A big part of project management is project selection. Each student will propose a unique project to be done as part of this class. Projects must have a sponsor (can be a student, friend, boss, community leader, yourself, etc.), provide a needed service or product, and be a good fit for this class.  Each student normally spends between 20-40 hours on the class project. Write a proposal for a potential project, using the potential project template (from the zip file with all templates) on the book’s website. Talk to the sponsor before writing the proposal if you really want to do it. The sponsor must contact me via email or phone if we decide to do that project within a couple of days. If you do not do a real project, you will work on a case study. Proposals must be typed and complete to get full credit.

HW3:  MBTI (100 points)

Take the MBTI test and research information on this tool, especially as it applies to team-building and individual work styles. (We’ll discuss it more in Chapter 6.) There are several websites that have different versions of the test and information on it, such as www.humanmetrics.com (the one you must take the test on for this HW), www.personalitytype.com, myersbriggs.com, and www.keirsey.com. You can also take the full-blown MBTI test through the career services office on campus. Write a one- to two-page single-spaced paper (600-1200 words) describing and analyzing your MBTI type (including the percentage for each letter), how this test is used as a team-building tool, and your opinion of its value/validity. Include footnotes citing at least three references. Put the word count at the top of the page. Also be sure to let your project manager know the four letters of your type for your first progress report.

HW4: Project 2016 Exercise 1 (100 points)

You can use a free online trial of Project 2016 or use it on the PCs at school or via remote access (See link in Moodle). Read and follow the hands-on instructions from the Brief Guide to Using Project 2016, found in Appendix A of the text.  As you perform the steps (end at page 414 for Exercise 1), press the Prnt Scrn button on your computer to show just the required screens (A-11, A-16, and A-23), and then paste the results into Microsoft Word or other word processing software. Also create your own file for part d and take a screen shot of it. Just load one file for this assignment into Moodle, clearly labeling each part. Each item/letter is worth 25 points. You must type everything for this assignment on your own (you can sit side by side and work on it), and your exam will include some basic info on Project 2016.

HW 5: Project 2016 Exercise 2 (100 points)

Finish the rest of Appendix A. Do Exercise 2 on p. 451. Again use Prnt Scrn to show your screen shots, and put everything in one file.

HW6: Histograms, Earned Value, and Quality Charts (100 points)

In order to prepare for a few questions on Exam 2, search the Internet for examples of a project resource histogram (see Chapter 5), an earned value chart (see Chapter 7), and at least two different quality charts (see Chapter 7). Write a short paper describing each chart, what it shows, and how it can assist in managing a project. Include a screen shot of each chart, along with a reference. Be sure the references are cited properly (author, date, title, as well as url, not just a url).

HW7:  Lessons Learned/Self-Assessment (100 points)

- Prepare your own lessons learned report (1-2-pages, single-spaced) based on personal reflections of what you learned from this class, including the team projects and presentations. Do not use the lessons learned template! (50 points).

- Write a 1-2-page self-assessment based on the team project, answering the following questions (50 points):

- If you had to give your team a grade for the project, what would it be?  Why?

- What were your roles and responsibilities on the group project?  How well do you think you performed on this project?

- Briefly assess each team member’s performance.  If you had to give each person, including yourself, a grade, what would it be?  To compare individual contributions, if you had 100 points to allocate to your team, how would you allocate them?

Extra Credit Homework:  For an extra 100 points (due the day of final exams), summarize an article that describes the results of a recent research study (done in the last three years) related to project management that is at least 8 pages long.  Write a two to three-page single-spaced paper (1,000 – 1,500 words) summarizing the study and your opinion of it.  Include footnotes with reference information.  Be sure the references have an author and a date. The extra points will be applied to your homework score.  100% is the maximum homework percentage.

DRAFT CLASS SCHEDULE

We’ll add individual presentations to the schedule as soon as possible, and I’ll post updated schedules in Moodle.  We’ll try to spread presentations out and have them fit in with lecture topics. Note that we will not meet every class period (online classes are shaded), but assignments, quizzes, and online activities will be due. Submit all assignments through Moodle, and work on your team projects and post results to your Google site or other team website. Note due dates and times.

| Date | Topic | Readings - HW Due and Quizzes | Presenter(s) |
| --- | --- | --- | --- |
| 1/13 | Course introduction, class survey, Ch. 1: Introduction to Project, Program, and Portfolio Management |  |  |
| 1/15 | Continue Ch. 1 | Read Chapter 1 |  |
| 1/20 | Review HW1 Plan presentations, discuss HW 2 ideas Intro to Ch. 2, Project, Program, and Portfolio Selection | Read Chapter 2 HW1: Summary of PM Websites and articles-submit in Moodle by noon |  |
| 1/22 | Review chapters 1-2, discuss HW2 ideas How to collaborate on documents How to give a great presentation | Quiz on ch. 1 and on 2 via Moodle before 4 PM | Volunteer 1 Volunteer 2 |
| 1/27 | Discuss project proposals and case studies for team projects Begin forming teams Ch. 3, Initiating | HW2: Project Proposal by noon Read Chapter 3 |  |
| 1/29 | Online class Continue forming teams | Quiz on ch. 3 and Online Activity 1 both by 4 PM Read Chapter 4 |  |
| 2/3 | Finalize projects and teams, set up team websites Ch. 4: Planning-part 1 | Email url of team website to me by noon |  |
| 2/5 | Online class Work on first progress report (hold kick-off meeting). Email or chat with me online with questions | Quiz on ch. 4 by 4 PM Team project charter and WBS for draft schedule due on team website by 4 PM. Read Chapter 5 |  |
| 2/10 | Ch. 5: Planning-part 2 Understanding MBTI and teams Review team project info and for Exam 1 See take-home part of Exam 1 in Moodle | HW3: MBTI by noon Quiz on ch. 5 by 4 PM | Volunteer 3 |
| 2/12 | Exam 1 (Chapters 1-5) |  |  |

| 2/17 | Online class Email or chat with me online with questions | Hold a team meeting and post minutes on your team’s Google site by 4 PM. Work on other items for Progress Report 1. |  |
| --- | --- | --- | --- |
| 2/19 | Team Progress Report 1. See info required in Appendix C, also in Moodle under Resources. | Have all documents on team site before class | Team PMs or designees |
| 2/24 | Online class Email or chat with me online with questions | Receive my feedback on PR 1 by noon, discuss as a team and document discussion, and make changes as needed on Google site by 4 PM. |  |
| 2/26 | Ch. 6: Planning – part 3 Project 2013 intro | Read Chapter 6 |  |
| 3/3 | Online class | Quiz on ch. 6 by 4 PM Read App A – start on HW4. Don’t put this one off! |  |
| 3/5 | Ch. 7: Executing Other pres? | HW4: MS Project Ex. 1 by noon, Read Chapter 7 |  |
| 3/10 | Ch. 7 (continued) Other pres? Perhaps start Ch. 7 | Quiz on ch. 7 by 4 PM |  |
| 3/12 | Online class | Start on HW5 and meet with your project team before break |  |
| 3/16-3/20 | No classes. Spring break. |  |  |
| 3/24 | Ch. 8: Monitoring and Controlling | Read Chapter 8 HW5: MS Project Ex. 2 by noon |  |
| 3/26 | More on chapter 8, time for teams | Quiz on ch. 8 by 4 PM and prepare for PR2 |  |
| 3/31 | Team Progress Report #2. See info required in Appendix C, also in Moodle under Resources. |  | Other team members? |
| 4/2 | Online class | Receive my feedback on PR 1 by noon, discuss as a team and document discussion, and make changes as needed on Google site by 4 PM. |  |
| 4/7 | Review charts Ch. 9: Closing Ch. 10 Best Practices in Project Management | HW6: Histograms, Earned Value, and Quality Charts by noon Read chs. 9-10 |  |
| 4/9 | Online class. Work on team projects | Quiz on chs. 9-10 due by 4 PM |  |

| 4/14 | Review for Exam 2 Other pres? Last day to present! |  |  |
| --- | --- | --- | --- |
| 4/16 | Exam 2 (Chapters 6-10, App A) |  |  |
| 4/21 | Team final presentations |  |  |
| 4/23 | Team final presentations |  | All final project notebooks due |
| 4/28 | Online class | HW 7: Lessons learned/self-assessment Extra credit HW and quiz due by 4 PM, fill out course evals |  |

PRESENTATION FEEDBACK FORM

Presenter(s):	___________________________________________

Topic:		___________________________________________	Date:	______________

Please circle a score (1-5) for each main area (shaded in gray) and provide comments as well.

Poor		Fair	    Good      Excellent        Outstanding

| CONTENT |  | 1 2 3 4 5 |
| --- | --- | --- |
| Well organized Introduction with overview Body Conclusion Clear thesis Well prepared Good flow Solid examples and relate material to class Good references (noted on slides/handout) Appropriate language/content |  |  |
| DELIVERY |  | 1 2 3 4 5 |
| Good eye contact (looked at audience most of the time) Good voice No distracting mannerisms Fluent and confident Natural gestures Good audio/visual aids Good use of technology |  |  |
| RESPONSE |  | 1 2 3 4 5 |
| Listened to audience Aware of audience Built-in engagement Discerned audience’s understanding Kept audience interested Responded well to questions Defended or modified position |  |  |
| OVERALL |  | 1 2 3 4 5 |

Note: Hard copy provided and file posted in Moodle? Refs cited properly? 5 points for each.

BEST PART OF PRESENTATION:

SUGGESTIONS FOR IMPROVEMENT: